## Al-Nasr Sport Hall
Promoting Inclusion and Social Change through Sports in Yemen
Rehabilitaion of Al-Nasr sport hall, Al-Dhale'e district, Al-Dhale'e governorate
# | Item Description | Implementation period/Works schedule
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
1.1 | Site delivery work | bar: Implementation period/Works schedule W1
1.2 | Metal roofing and siding works | bar: Implementation period/Works schedule W2 to Implementation period/Works schedule W7
1.3 | Electrical Works | bar: Implementation period/Works schedule W6 to Implementation period/Works schedule W7
1.4 | Door and windows installation works | bar: Implementation period/Works schedule W6 to Implementation period/Works schedule W7
15 | Plastering and painting works | bar: Implementation period/Works schedule W7 to Implementation period/Works schedule W9
1.6 | Hall floor works | bar: Implementation period/Works schedule W8 to Implementation period/Works schedule W10
1.7 | Works designed for people with disabilities | bar: Implementation period/Works schedule W8 to Implementation period/Works schedule W9
1.8 | Handover the project | bar: Implementation period/Works schedule W11

## Al-Hawtah Sport Gymnasium
Promoting Inclusion and Social Change through Sports in Yemen
Rehabilitaion of Al-Hawtah sport gymnasium, Al-Hawtah district, Lahj governorate
# | Item Description | Implementation period/Works schedule
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
1.1 | Site delivery work | bar: Implementation period/Works schedule W1
1.2 | Polycarbonate Skylights works on the gym roof
1.3 | Painting works
1.4 | Windows , gates and Iron protection works
1.5 | Sanitary works for 2 latrines
1.5 | Audience chairs Works | bar: Implementation period/Works schedule W6 to Implementation period/Works schedule W7
1.6 | Works designed for people with disabilities | bar: Implementation period/Works schedule W4 to Implementation period/Works schedule W5
1.7 | Handover the project | bar: Implementation period/Works schedule W8