Annex B

PR2406007

Statement of Work: Yakhtul Water Project Rehabilitation

**Location:** Yakhtul Community, Mocha District, Taiz Governorate

**Description:**

* The selected contractor will complete all works necessary to rehabilitate the Yakhtul water system per the BOQs and drawings and according to the instructions of the supervising engineer from Samaritan’s Purse. The key activities are:
	+ Supply and install the 6” HDPE pumping line
	+ Rehabilitation of the water tower tank (100 m3)
	+ Supply and install distribution pipe network

**Timeline Requirements:**

* The contractor will be held to the quoted timeline submitted as part of Annex A. The timeline will begin from site handover and the project must be completed within the quoted time.
* A one-week grace period may be granted based on needs.
* The contractor is required to submit a weekly progress report to Samaritan’s Purse based on the implementation plan provided as part of Annex A.

**Payment Plan:**

* Project will be paid in installments per the below:
* 50% of the total contract value will be paid upon 70% completion of BOQ A. *This will be measured by the installation of* ***Item No. 1.0 in BOQ A*** *with its associated valves and fittings.*
* 40% of the total contract value will be paid upon 100% completion of ALL BOQs.
* 10% will be withheld for one year after final site handover for the warranty period.

**Site Visit**

* A site visit ***with Annex G* *signed and stamped by the community committee*** is required to submit a quote. Please find relevant information in the tables below.

|  |  |
| --- | --- |
| **Location** | **GPS Coordinates** |
| Yakhtul Community and tower tank | 13°26'48.15"N, 43°16'31.91"E |
| Al Zaini village | 13°26'21.95"N, 43°18'25.80"E |
| Beginning of pumping line | 13°26'55.05"N, 43°20'36.74"E |

|  |  |
| --- | --- |
| **Local Point of Contact** | **Phone Number** |
| Salah Al Shathli | +967 773139743/738559495 |

**Contract and BOQs**

* No changes to the BOQs shall be made or additional works authorized without written approval from the organization and the contractor.
* Daily workers for the project should be hired from the local community.

|  |
| --- |
|  |

**All documents listed in Annex A must be submitted in the bid.**

 Stamp